## Slide 1: Predicting Songs that Top the Charts
11/11/2020
Scott Fiene

## Slide 2: Project Description & Scope
Overview
  Music is a big industry and there are many varieties, genres, and forms. Most music is held to the constraint of how good the song is by how well it does in the various mediums that provide rewards. There are The Grammy’s, Billboard Charts, gold and platinum records, and too many others to list. Within all of these award ceremonies, there are categories representing the different genres of music and what are the top ranked songs in that context.
  All songs can be broken down into certain aspects that make up the song such as tempo, speechiness, liveness, and acousticness to name a few. These terms come from the Spotify API and a dataset that they created for a Kaggle competition. These aspect of each song hold the potential to be able to determine what makes that songs popular or not, a chart topper or not.
  It would be out of the scope of this project and the time frame of this project to build something of this magnitude, but it would be doable. Instead, this project zooms in and focuses on a certain time frame.
Project Description
  This project will look at songs that made the Billboard charts between the dates of 1950 and 2020 and analyze all their attributes to create a predictive model. Once the model is trained, it will be able to predict whether a song will make the charts or not.
Scope
  The scope of this project includes a conservative dataset. The training set is a joining of 4 separate dataset, 2 contain songs that charted and 2 contain songs that did not chart. They are cleaned and joined together to form a training set of ~1000 rows. The test set is cleaned to reflect the training set and filtered down to have ~1000 rows as well

## Slide 3: Sponsors, Stakeholders, Roles, Responsibilities, and Business Case
Sponsors
  Venture Capitalists, Music Producers and/or Recording Studio Owners, App Company
Stakeholders
  Venture Capitalist, App Company
Roles & Responsibilities
  Data gathering, mining, analysis, and modeling done by Scott Fiene
Business Problem
  Recording studios only go on the producer's instinct when it comes to producing hit songs. For some producer’s that is ok because of their expertise in the industry (thinking about Dr. Dre & Jay-Z), but for others it might not come as easy. This product may help those producers and studios
Benefits
  The benefits from the creation of this product would greatly improve the identification of songs that have a high probability of hitting the charts. This has a two-fold benefit of making it easier to market and creating greater income for all people involved
Budget
  Data gathering, mining, analysis, and modeling – 12 hours a week for 8 weeks at $100/hour -- $9600**
  **No licensing fees required as this is an academic project

## Slide 4: Key Milestones & Deliverables High Level Project Management Overview
# | Milestone | Key Tasks and Deliverables | Start Date | End Date
1 | Business Understanding | Access the Situation Determine Business Objectives Determine Data Requirements Complete Project Charter | 10/25/2020 | 11/07/2020
2 | Data Understanding | Verify Data Quality Collect Initial Data Describe Data Explore Data | 11/01/2020 | 11/14/2020
3 | Data Preparation | Select Data Clean Data Construct Data Integrate Data Format Data | 11/01/2020 | 11/21/2020
4 | Modeling Phase | Select Tool Select Modeling Technique Generate Test Design Build Model Parameter Settings Assess the Model | 11/08/2020 | 12/05/2020
5 | Evaluation Phase | Evaluate Results Review the Model and Process Determine Next Steps | 11/22/2020 | 12/12/2020
6 | Deployment Phase | Plan Deployment Plan Monitoring Maintenance Review Project Produce Final Report | 12/14/2020 | 12/19/2020

## Slide 5: Key Milestones & Deliverables Drilled Down Project Management Overview
# | Milestone | Key Tasks and Deliverables | Start Date | End Date
1 | Business Understanding | Provide overview on the various aspects related to a song according to Spotify Clearly define the audience, approach on analysis, and end goals to meet Gain high level understanding of the data and determine expectations Create Project Charter | 6/4/2018 | 6/16/2018
2 | Data Understanding | Gather Spotify song data and Top 500 song list Obtain supplemental Billboard charts data and Grammy data Perform initial exploratory analysis of the data Verify quality of data and noting anomalies | 6/17/2018 | 6/23/2018
3 | Data Preparation | Clean all data sets and organize them to be identical to each other Make all attributes the same type across all datasets Handle missing values, outliers, and anomalies from the previous phase Merge cleaned dataset together Determine the most useful attributes Split data into training and test sets | 6/24/2018 | 6/30/2018
4 | Modeling Phase | Run various models with default parameters to get idea of performance Assess model performance and reiterate data preparation phase as needed Narrow down to highest performing model Fine tune the parameters of the model to maximize its performance Apply model to the test set and assess predictive performance Reiterate phase 3 and 4 as needed until model is sufficiently tuned | 7/1/2018 | 7/14/2018
5 | Evaluation Phase | Apply model to the test set and assess predictive performance Reiterate phase 3, 4, and 5 as needed until model is sufficiently Check whether model has answered business questions and criteria | 7/15/2018 | 7/21/2018
6 | Deployment Phase | Deploy model to production Continually monitor and adjust model and data as needed to keep up performance Produce final written report | 7/22/2018 | 7/28/2018

## Slide 6: Critical Success Factors & Risks
Critical Success Factors
This project must be completed by 12/19/2020
The project must include a model simulator
Risks Constraints & Assumptions
The project assumes that there is a way for Spotify to analyze songs in real time to obtain the numbers needed to input into the model for prediction
The project is only for the people work for, produce, or own recording studios
This project assumes that there is funding enough to build this model and package it into an app for demo and use
This project is not specific to Spotify, so if any other company could analyze songs real time then it would stand to reason that it would be ok to use their music analysis software real-time and not Spotify
Risk Impact
  Project Size: Small (approx. 120 hours)
  Change Management: Low (scope is clearly defined; only change expected would be the song analysis software)
  Training/Communication: High (model will need to be explained to sponsor and stakeholders, training on the final product and song analysis software for the end user)