## Project Dashboard
| Phase Gates and Exit Criteria: CRISP | Status | Percentage Completed | Planned Start Date | Planned Finish Date | Actual Finish Date | Notes
| Overall Project | Complete | 100% | 2020-10-25 | 2020-12-19 | 0
Phase 1 | Phase 1: Business Understanding | Complete | 100% | 2020-10-25 | 2020-11-07 | 0
1.1 | Determine business objectives | Complete | 100% | 2020-10-25 | 2020-11-07 | 0
1.2 | Assess the situation | Complete | 100% | 2020-10-25 | 2020-11-07 | 0
1.3 | Determine data mining goals | Complete | 100% | 2020-10-25 | 2020-11-07 | 0
1.4 | Project management | Complete | 100% | 2020-10-25 | 2020-11-07 | 0
Phase 2 | Phase 2: Data Understanding | Complete | 100% | 2020-11-01 | 2020-11-14 | 0
2.1 | Collect initial data | Complete | 100% | 2020-11-01 | 2020-11-14 | 0
2.2 | Describe data | Complete | 100% | 2020-11-01 | 2020-11-14 | 0
2.3 | Explore data | Complete | 100% | 2020-11-01 | 2020-11-14 | 0
2.4 | Verify data quality | Complete | 100% | 2020-11-01 | 2020-11-14 | 0
Phase 3 | Phase 3: Data Preparation | Complete | 100% | 2020-11-01 | 2020-11-21 | 0
3.1 | Select data | Complete | 100% | 2020-11-01 | 2020-11-21 | 0
3.2 | Clean data | Complete | 100% | 2020-11-01 | 2020-11-21 | 0
3.3 | Construct data | Complete | 100% | 2020-11-01 | 2020-11-21 | 0
3.4 | Integrate data | Complete | 100% | 2020-11-01 | 2020-11-21 | 0
3.5 | Format data | Complete | 100% | 2020-11-01 | 2020-11-21 | 0
3.6 | Describe data | Complete | 100% | 2020-11-01 | 2020-11-21 | 0
Phase 4 | Phase 4: Modeling | Complete | 100% | 2020-11-08 | 2020-12-05 | 0
4.1 | Select modeling techniques | Complete | 100% | 2020-11-08 | 2020-12-05 | 0
4.2 | Select modeling and analytical tools | Complete | 100% | 2020-11-08 | 2020-12-05 | 0
4.3 | Generate model test design | Complete | 100% | 2020-11-08 | 2020-12-05 | 0
4.4 | Build model parameter settings | Complete | 100% | 2020-11-08 | 2020-12-05 | 0
4.5 | Assess the model | Complete | 100% | 2020-11-08 | 2020-12-05 | 0
Phase 5 | Phase 5: Evaluation | Complete | 100% | 2020-11-22 | 2020-12-12 | 0
5.1 | Evaluate results | Complete | 100% | 2020-11-22 | 2020-12-12 | 0
5.2 | Approve models | Complete | 100% | 2020-11-22 | 2020-12-12 | 0
5.3 | Determine next steps | Complete | 100% | 2020-11-22 | 2020-12-12 | 0
Phase 6 | Phase 6: Deployment | Complete | 100% | 2020-12-06 | 2020-12-19 | 0
6.1 | Plan deployment | Complete | 100% | 2020-12-06 | 2020-12-19 | 0
6.2 | Plan monitoring, maintenance and attainment of value propositions | Complete | 100% | 2020-12-06 | 2020-12-19 | 0
6.3 | Produce final report | Complete | 100% | 2020-12-06 | 2020-12-19 | 0
6.4 | Review Project | Complete | 100% | 2020-12-06 | 2020-12-19 | 0

## Phase 1. Business Understanding
| Exit Criteria and Deliverables | Status | Percent Complete | Planned Start Date | Planned Finish Date | Actual Start Date | Actual Finish Date | Notes
1.1 | Determine Business Objctives | Complete | 100% | 2020-10-25 | 2020-11-07 | 0 | 0
1.1.1 | Identify business and project objectives | Complete | 100% | 2020-10-25 | 2020-11-07
1.1.2 | Identify business success criteria | Complete | 100% | 2020-10-25 | 2020-11-07
1.1.3 | Understand background | Complete | 100% | 2020-10-25 | 2020-11-07
1.2 | Assess the Situation | Complete | 100% | 2020-10-25 | 2020-11-07 | 0 | 0
1.2.1 | Identify value propositions and determine costs and benefits -ROI | Complete | 100% | 2020-10-25 | 2020-11-07
1.2.2 | Create dictionary of terminology | Complete | 100% | 2020-10-25 | 2020-11-07
1.2.3 | Identify risks and contingencies | Complete | 100% | 2020-10-25 | 2020-11-07
1.2.4 | Inventory resources requirements assumptions and constraints | Complete | 100% | 2020-10-25 | 2020-11-07
1.3 | Determine Data Mining Goals | Complete | 100% | 2020-10-25 | 2020-11-07 | 0 | 0
1.3.1 | Identify data mining goals | Complete | 100% | 2020-10-25 | 2020-11-07
1.3.2 | Identify data mining success criteria | Complete | 100% | 2020-10-25 | 2020-11-07
1.4 | Project Management | Complete | 100% | 2020-10-25 | 2020-11-07 | 0 | 0
1.4.1 | Perform initial assessment of tools and techniques | Complete | 100% | 2020-10-25 | 2020-11-07
1.4.2 | Create Project Plan | Complete | 100% | 2020-10-25 | 2020-11-07
1.4.3 | Create Project Charter | Complete | 100% | 2020-10-25 | 2020-11-07

## Phase 2. Data Understanding
| Exit Criteria and Deliverables | Status | Percent Complete | Planned Start Date | Planned Finish Date | Actual Start Date | Actual Finish Date | Notes
2.1 | Collect Initial Data | Complete | 100% | 2020-11-01 | 2020-11-14 | 0 | 0
2.1.1 | Initial data report. Describe sampling if used. | Complete | 100% | 2020-11-01 | 2020-11-14
2.2 | Describe data | Complete | 100% | 2020-11-01 | 2020-11-14 | 0 | 0
2.2.1 | Data description report | Complete | 100% | 2020-11-01 | 2020-11-14
2.3 | Explore data | Complete | 100% | 2020-11-01 | 2020-11-14 | 0 | 0
2.3.1 | Data exploration report | Complete | 100% | 2020-11-01 | 2020-11-14
2.4 | Verify data quality | Complete | 100% | 2020-11-01 | 2020-11-14 | 0 | 0
2.4.1 | Data quality report | Complete | 100% | 2020-11-01 | 2020-11-14

## Phase 3. Data Preperation
| Exit Criteria and Deliverables | Status | Percent Complete | Planned Start Date | Planned Finish Date | Actual Start Date | Actual Finish Date | Notes
3.1 | Clean Data | Complete | 100% | 2020-11-01 | 2020-11-21 | 0 | 0
3.1.1 | Data cleaning report | Complete | 100% | 2020-11-01 | 2020-11-21
3.2 | Construct Data | Complete | 100% | 2020-11-01 | 2020-11-21 | 0 | 0
3.2.1 | Report on derived attributes and generated records | Complete | 100% | 2020-11-01 | 2020-11-21
3.3 | Describe Data | Complete | 100% | 2020-11-01 | 2020-11-21 | 0 | 0
3.3.1 | Updated dataset description report | Complete | 100% | 2020-11-01 | 2020-11-21
3.4 | Format the Data | Complete | 100% | 2020-11-01 | 2020-11-21 | 0 | 0
3.4.1 | Report on formatting the data | Complete | 100% | 2020-11-01 | 2020-11-21
3.5 | Integrate Data | Complete | 100% | 2020-11-01 | 2020-11-21 | 0 | 0
3.5.1 | Report on merged records | Complete | 100% | 2020-11-01 | 2020-11-21
3.6 | Select Data | Complete | 100% | 2020-11-01 | 2020-11-21 | 0 | 0
3.6.1 | Report on rationale for inclusion/exclusion | Complete | 100% | 2020-11-01 | 2020-11-21

## Phase 4. Modeling
| Exit Criteria and Deliverables | Status | Percent Complete | Planned Start Date | Planned Finish Date | Actual Start Date | Actual Finish Date | Notes
4.1 | Select Modeling Techniques | Complete | 100% | 2020-11-08 | 2020-12-05 | 0 | 0
4.1.1 | Report on modeling technique and modeling assumptions | Complete | 100% | 2020-11-08 | 2020-12-05
4.2 | Select Modeling and Analytical Tools | Complete | 100% | 2020-11-08 | 2020-12-05 | 0 | 0
4.2.1 | Report on tools to be used | Complete | 100% | 2020-11-08 | 2020-12-05
4.3 | Generate Model Test Design | Complete | 100% | 2020-11-08 | 2020-12-05 | 0 | 0
4.3.1 | Report on the design | Complete | 100% | 2020-11-08 | 2020-12-05
4.4 | Build Model ParameterSettings | Complete | 100% | 2020-11-08 | 2020-12-05 | 0 | 0
4.4.1 | Report on parameter settings | Complete | 100% | 2020-11-08 | 2020-12-05
4.5 | Assess the Model | Complete | 100% | 2020-11-08 | 2020-12-05 | 0 | 0
4.5.1 | Report on model assessment and any revised parameters | Complete | 100% | 2020-11-08 | 2020-12-05

## Phase 5. Evaluation
| Exit Criteria and Deliverables | Status | Percent Complete | Planned Start Date | Planned Finish Date | Actual Start Date | Actual Finish Date | Notes
5.1 | Evaluate Results | Complete | 100% | 2020-11-22 | 2020-12-12 | 0 | 0
5.1.1 | Align assessment of data mining results with business success criteria- Provide report | Complete | 100% | 2020-11-22 | 2020-12-12
5.2 | Approve Models | Complete | 100% | 2020-11-22 | 2020-12-12 | 0 | 0
5.2.1 | Report on approval sign off on models and process | Complete | 100% | 2020-11-22 | 2020-12-12
5.3 | Determine Next Steps | Complete | 100% | 2020-11-22 | 2020-12-12 | 0 | 0
5.3.1 | Create List of possible actions | Complete | 100% | 2020-11-22 | 2020-12-12
5.3.2 | Validate value propositions | Complete | 100% | 2020-11-22 | 2020-12-12
5.3.3 | Create list of decisions | Complete | 100% | 2020-11-22 | 2020-12-12

## Phase 6. Deployment
| Deliverables | Status | Percent Complete | Planned Start Date | Planned Finish Date | Actual Start Date | Actual Finish Date | Notes
6.1 | Plan Deployment | Complete | 100% | 2020-12-06 | 2020-12-19 | 0 | 0
6.1.1 | Update project plan to include deployment activities | Complete | 100% | 2020-12-06 | 2020-12-19
6.2 | Plan Monitoring, Maintenance and Attainment of Value Propositions | Complete | 100% | 2020-12-06 | 2020-12-19 | 0 | 0
6.2.1 | Update plan to drive value propositions to realization | Complete | 100% | 2020-12-06 | 2020-12-19
6.2.2 | Update project plan to include monitoring and maintenance activities | Complete | 100% | 2020-12-06 | 2020-12-19
6.3 | Produce Final Report | Complete | 100% | 2020-12-06 | 2020-12-19 | 0 | 0
6.3.1 | Submit final report | Complete | 100% | 2020-12-06 | 2020-12-19
6.4 | Review Project | Complete | 100% | 2020-12-06 | 2020-12-19 | 0 | 0
6.4.1 | Close out project deliverables | Complete | 100% | 2020-12-06 | 2020-12-19
6.4.2 | Document the experience | Complete | 100% | 2020-12-06 | 2020-12-19
6.4.3 | Lessons learned | Complete | 100% | 2020-12-06 | 2020-12-19
6.4.4 | Deliver presentation and begin project execution | Complete | 100% | 2020-12-06 | 2020-12-19
6.4.5 | Archive project artifacts | Complete | 100% | 2020-12-06 | 2020-12-19

## Data Mining Competencies
Data Mining Competencies
ID | Description | Stage
1 | Determine business objectives including background of the business process, business objectives, success criteria, relevant KPI's. | Business Understanding
2 | Assess the situation including an inventory of resources, requirements, assumptions, constraints, risks contingencies, terminology. | Business Understanding
3 | Determine data mining goals including a problem statement, targeted costs and benefits, customer expectations and success criteria.Business sponsors who need the analytic solution define the problem, project objectives and solution requirements from a business perspective. | Business Understanding
4 | Create a project charter and project plan. Identify project management team and tools. | Business Understanding
5 | Perform initial check of data availability and perform initial data collection including sampling from population as appropriate. | Develop Analytic Approach and Data Understanding
6 | Review the available data against the project objectives and identify a preliminary analytical approach as well as any additional data requirements relevant for the analysis. | Develop Analytic Approach and Data Understanding
7 | Describe the data set fields using summary statistics | Develop Analytic Approach and Data Understanding
8 | Refine the data set to include both structured and unstructured elements (i.e. text or symbols). Convert unstructured data into structured fields and indicators that are useful for analysis. | Develop Analytic Approach and Data Understanding
9 | Perform exploratory analysis using statistical and visualization methods such as correlation, cluster analysis, principle components analysis, plotting etc. with the aim of identifying patterns of associations and uncovering models within the data. | Develop Analytic Approach and Data Understanding
10 | Create hypotheses using abductive reasoning based upon the preliminary findings from exploratory data analysis. | Develop Analytic Approach and Data Understanding
11 | Review the data and verify data quality and validity of the source | Develop Analytic Approach and Data Understanding
12 | Select data to be used for model building and hypothesis testing. Provide rational for inclusion and exclusion. | Data Preparation
13 | Cleanse the data as appropriate ensuring proper treatment of missing values, consistent naming conventions etc. and the ability to load from disparate data warehouse systems. | Data Preparation
14 | Select and create variables for hypothesis testing. | Data Preparation
15 | As appropriate transform data for proper model fitting using techniques such as removing outliers, logarithmic transformation for removal of heteroscedasticity etc. | Data Preparation
16 | As appropriate generate new variables that are needed for model building and testing by generating derived attributes such as indicator variables. | Data Preparation
17 | Integrate, merge and join data fields from disparate data warehouse systems as required. | Data Preparation
18 | Select predictive or descriptive modeling techniques such as neural networks, tree based approaches, logistic/regression based approaches, etc in accord with the overall analytical approach for the project. Validate the approach and assumptions with the objectives of the project. | Modeling
19 | Generate the test design using deductive reasoning to ensure that results will either support or refute hypotheses. | Modeling
20 | Build and execute models by performing parameter estimation using the data set (and in the case of having reliable prior knowledge use bayesian methods to augment existing data). | Modeling
21 | Assess, refine and iterate the model and the data set as appropriate to find the best model for the variables. | Modeling
22 | Evaluate the model to understand its quality and ensure that it properly and fully addresses the business problem. Iterate modeling as necessary. | Evaluation
23 | Compute various diagnostic measures and other outputs such as tables and graphs to interpret the model's quality and efficacy in solving the business problem. For a predictive model use a testing set which is independent of the training set but follows the same probability distribution and has a known outcome. | Evaluation
24 | Evaluate the results and use inductive reasoning to extend the generalizability of the results to business conclusions and actions. Align results of data mining with business success criteria. | Evaluation
25 | Deploy model to the business in a limited way (such as a pilot) to test business efficacy and generalizability. Assess pilot and refine as required. Ensure proper training to business users. | Evaluation
26 | Develop a list of possible actions and drive key business decisions to closure that ensure attainment of business objectives. | Evaluation
27 | Approve the model for full scale deployment and create a deployment project plan. The plan should include user training and data governance to maintain integrity of the model. | Deployment
28 | Deploy the model into an operational business process. Execute the project plan and drive business value. | Deployment
29 | Create a closeout report that summarizes results, actions and lessons learned. Present final report to business sponsors. | Deployment
30 | Obtain ongoing feedback related to model performance and update/adjust as appropriate. | Deployment